Board of Works Meeting – July 11, 2023

To: Board of Works

Clerk Treasurer’s Office

I respectfully request the Board of Works approve the proposal from Vail’s concrete for the difference in price from 7 inches on concrete to 10 inches of concrete on Broadway St. At the last Board meeting you approved the repair of $153,568.50. Before construction we did some test holes and dug down beside the street trying to estimate the thickness and believed it to be an average of 7 inches. When construction began last week we noticed quickly that the street is much thicker at an average of 10 inches. This is a good thing as far as the life expectancy of a highly traveled street but it does make repairs more expenses. The new proposal is $244,049.40, so I am asking the board approve the difference of $90,480.90. This is a material bid price. If you have any question please feel free to contact me. Thank you.

Tyler Rankins

Street Commissioner